FortuneMarq Build Project Folder Report Purpose · What's Done · What's Pending

Generated: April 29, 2026  |  FortuneMarq Media & Marketing, Hubli

| 13 Total Folders | 1 Critical Blocker | ₹0 Current MRR (Pre-Revenue) |
| --- | --- | --- |

# Project Overview

FortuneMarq Build is the complete operating system for FortuneMarq Media & Marketing. It is organised into 13 folders spanning CRM development, sales content, client delivery, market data, finance, legal, and brand. As of April 29, 2026, the business is pre-revenue. All systems are built and content-complete. The single remaining blocker across virtually every folder is the deployment of FMOS (the CRM) to Hostinger.

| Folder | One-Line Summary | Status |
| --- | --- | --- |
| 00_MASTER | Master strategy docs, brand assets, and universal project instructions | COMPLETE |
| 01_CRM_AND_TOOL | FMOS — the full Next.js CRM. Production-ready v4.5. Awaiting deployment. | PRODUCTION READY |
| 02_SERVICE_DELIVERY_AUTOMATION | Ads, SEO, and website automation systems — all blocked on FMOS deployment | NOT STARTED |
| 03_SALES_SYSTEM | Telecaller scripts, WhatsApp templates, proposals, and agreements — fully built | COMPLETE |
| 04_CLIENT_MANAGEMENT | Onboarding SOPs, monthly reports, upsell system — fully built | COMPLETE |
| 05_FORTUNEMARQ_ONLINE_PRESENCE | Website live, 11 niche landing pages built but not deployed, social media not started | IN PROGRESS |
| 06_PAID_MARKETING | Google Ads and Meta Ads strategy — not started, waiting for FMOS + landing pages | NOT STARTED |
| 07_DATA_AND_RESEARCH | 858 Hubli leads ready, 75 PDFs generated, keyword data for 9 cities complete | IN PROGRESS |
| 08_FINANCE | Pricing locked, FMOS finance module built — awaiting deployment to go live | IN PROGRESS |
| 09_LEGAL_AND_OPERATIONS | GST registered, agreement templates and policies complete. Minor items remain. | COMPLETE |
| 10_PERSONAL_GROWTH | Three learning tracks defined — no logs or resources added yet | NOT STARTED |
| Brand_Assets | All logo files and brand fonts — complete and shared across project | COMPLETE |
| obsidian-rag | Claude-powered knowledge base / wiki — 17 pages covering all business context | COMPLETE |

| 00 MASTER | COMPLETE |
| --- | --- |

PURPOSE: The strategic hub of the entire project. Contains the master business plan, content hierarchy, Claude operating instructions, and brand assets. Everything else in the project is built from the blueprints here.

Key Files & Subfolders - Agency_OS_Master_Plan.docx — Master business and operations plan - FortuneMarq_Master_Blueprint.docx — Full agency blueprint - FortuneMarq_Content_Hierarchy.docx — L0–L7 content architecture - MASTER_CONTEXT.md — Living context file updated each session - UNIVERSAL_PROJECT_PROMPT.md — Claude session start prompt - Claude_Project_Instructions.md — Instructions for Claude within this project - Brand_Assets/ — Logos (3 variants), brand fonts (Alliance, JetBrains Mono)

| ✅ Done - Master blueprint and content hierarchy documents complete - Universal project prompt and Claude instructions finalized - Brand assets (3 logo variants, 2 brand fonts) in place - Niche data reference sheet complete with real Google Keyword Planner volumes - Full system map, team, tech stack, and revenue targets documented - MASTER_CONTEXT.md kept up to date through all sessions | ⏳ Pending - No outstanding items — this folder is reference-only - Update MASTER_CONTEXT.md each session as decisions are made |
| --- | --- |

| 01 CRM AND TOOL (FMOS) | PRODUCTION READY |
| --- | --- |

PURPOSE: FMOS (FortuneMarq Operating System) — the custom-built CRM at the centre of the business. Built in Next.js + Supabase. Manages leads, outreach, proposals, agreements, onboarding, invoicing, and team roles. v4.5 is production-ready and awaiting deployment to fmos.fortunemarq.com.

Key Files & Subfolders - fmos/ — Full Next.js application (35+ modules, admin dashboard) - FMOS_Change_Specs/ — Phase A–E specs with all 21 data JSON/TS files - Antigravity_Prompts/ — Phase-by-phase build prompts used to develop FMOS - _project_files/ — Application documentation and master context - CONTEXT.md — CRM-specific session context

| ✅ Done - Full Next.js application built — 35+ admin modules - All 5 phases (A–E) of FMOS specs complete and implemented - All 21 data files (scripts, templates, proposals, agreements, onboarding) in FMOS_Change_Specs/data/ - 858 Hubli leads imported and live in the CRM - Bulk-import tool built at /admin/bulk-import for remaining ~6,300 leads - Real search volumes wired into TelecallerCockpit via searchVolumeMap - Telecaller scripts (A/B/C/D) updated with 'our founder' language - All API routes and server actions complete - All role-based views (Jabeer, Afifa, Zaid/Sufiyan) built | 🔲 Pending (Deployment Checklist) - Add OPENROUTER_API_KEY to Hostinger environment variables - Point fmos.fortunemarq.com subdomain to Hostinger server - Deploy the Next.js application to Hostinger - Create Afifa's telecaller account in /admin/users - Create Zaid and Sufiyan accounts - Run /admin/bulk-import to load remaining ~6,300 leads - Enter Austin Dental Spa and OM SAI TRAVELS real client data - Activate GST invoice settings with GSTIN 29ICWPS9816Q1ZS - Run SQL migrations for Phase C columns (outreach_stage, pdf_sent_at, etc.) - Seed WhatsApp templates into Supabase whatsapp_templates table (Phase D) |
| --- | --- |

| 02 SERVICE DELIVERY AUTOMATION | NOT STARTED |
| --- | --- |

PURPOSE: The automation layer for FortuneMarq's service delivery. Will contain three systems: a Website Brief App (for structured client intake), an Ads Automation engine, and an SEO Automation engine. None are built yet — all are waiting for FMOS to be deployed and clients to be onboarded first.

Key Files & Subfolders - Ads_Automation/ — Placeholder folder + CONTEXT.md - SEO_Automation/ — Placeholder folder + CONTEXT.md - Website_Design_and_Brief_App/ — Placeholder folder + CONTEXT.md - _project_files/ — Reference docs and master context - Agency_OS_Master_Plan.docx — Blueprint for the automation systems

| ✅ Done - Agency_OS_Master_Plan.docx — full automation roadmap documented - Phase sequence defined: Website Brief App first, then Ads, then SEO - Folder structure and CONTEXT.md files created - SOPs (L5 in content hierarchy) planned as blueprint for each system | 🔲 Pending - Website Brief App — Phase 1 (Months 1–2 after FMOS deployment) — NOT STARTED - Ads Automation Engine — Phase 2 (Months 3–4) — NOT STARTED - SEO Automation Engine — Phase 3 (Months 5–6) — NOT STARTED - Full automation + unified reporting — Phase 4 (Months 7–8) — NOT STARTED - SOPs for each service must be written first to blueprint automation - Blocked: All systems blocked on FMOS deployment - Blocked: Ads/SEO automation additionally blocked on having 5+ paying clients - Blocked: Website Brief App additionally blocked on Zaid + Sufiyan completing training |
| --- | --- |

| 03 SALES SYSTEM | COMPLETE |
| --- | --- |

PURPOSE: The complete outbound sales engine. Contains telecaller scripts (4 types), WhatsApp message templates (17 templates), proposal schema and data, agreement templates, and all onboarding content. L2 through L7 of the content hierarchy are complete. Everything is ready — execution is blocked on FMOS deployment.

Key Files & Subfolders - Telecaller_Scripts/ — 4 JSON scripts (A/B/C/D), FortuneMarq_Telecaller_Call_Flow.docx - Telecaller_Scripts/FMOS_Script_Data/ — TypeScript types and loaders - Telecaller_Scripts/Hubli/ — Niche-specific calling data for Hubli - WhatsApp_Templates/ — 17 templates across 5 JSON files - Proposals/ — Proposal schema, services_data.json, TypeScript types - Proposals/Sample_Proposal_Gyms_Hubli_TypeB.pdf — Sample PDF output - _project_files/ — Niche data reference sheet and master context

| ✅ Done - L2 — Telecaller Scripts — 4 types (A/B/C/D) with 9 outcomes each - L3 — WhatsApp Templates — 17 templates across 5 categories - L4a — Proposal Template — schema, services data, TypeScript types complete - L4b — Agreement Document — 1-page agreement with service-specific terms - L5 — Onboarding SOPs and checklists complete for all 7 services - L6 — Monthly report templates and client health score system built - L7 — Upsell rules and scripts built - Scripts updated: 'our founder' language, Zoom meeting ask, updated objection responses - Script loader TypeScript utility built for FMOS integration - Sample proposal PDF generated for Gyms niche (TypeB) | 🔲 Pending - Load all content into live FMOS once deployed - Seed WhatsApp templates into Supabase (Phase D spec) - Purchase and connect Meta WhatsApp Business API - Deploy niche landing pages (required for bot reply templates) - Afifa to begin calling from TelecallerCockpit after FMOS is live |
| --- | --- |

| 04 CLIENT MANAGEMENT | COMPLETE |
| --- | --- |

PURPOSE: All systems for managing clients after they sign. Covers onboarding (10-step SOP + per-service checklists), monthly reporting (schema + health score), and upselling (rules + scripts). L5, L6, and L7 of the content hierarchy are all complete. Zero clients yet — systems activate post-deployment.

Key Files & Subfolders - Onboarding/onboarding_sop.md — 10-step onboarding SOP - Onboarding/FMOS_Onboarding_Data/ — JSON checklists + TS types/loaders - Monthly_Reports/FMOS_Report_Data/ — Monthly report schema + health score JSON - Upsell_System/FMOS_Upsell_Data/ — Upsell rules + upsell scripts JSON - Renewals_and_Upsells/ — Renewal process folder (CONTEXT.md placeholder) - _project_files/ — Master context

| ✅ Done - L5a — 10-step Onboarding SOP complete (onboarding_sop.md) - L5b — Per-service onboarding checklists for all 7 services (onboarding_checklists.json) - L6a — Monthly report schema complete (monthly_report_schema.json) - L6b — Client health score system complete — 4 pillars: Rankings 25 + Traffic 25 + Leads 25 + GMB 25 - L7 — Upsell rules and scripts complete (upsell_rules.json + upsell_scripts.json) - TypeScript types and FMOS loaders built for all 3 data systems | 🔲 Pending - FMOS Phase D: Build onboarding tab with per-service task checklists in the CRM - FMOS Phase D: Asset vault for storing client credentials and files - FMOS Phase E: Build upsell queue in admin dashboard - Monthly PDF report generation directly from FMOS - Health score auto-calculation from live client data - Renewals alert: FMOS to alert Jabeer 30 days before renewal - All blocked on FMOS deployment |
| --- | --- |

| 05 FORTUNEMARQ ONLINE PRESENCE | IN PROGRESS |
| --- | --- |

PURPOSE: FortuneMarq's own digital presence — website, Google My Business, 11 niche landing pages, and social media. The website is live on Hostinger. The niche landing pages are built but not yet deployed. Social media (Instagram, LinkedIn) has not been started. Niche pages must go live before WhatsApp bot replies can be sent.

Key Files & Subfolders - public_html.zip — 40MB live website archive (fortunemarq.com) - niches/ — 11 HTML landing pages (car-rentals, dental, gyms, ielts, interior, ivf, jee-neet, kitchens, real-estate, skin, tuition) - assets/images/ — Brand visual assets - Instagram_Facebook/ — Subfolders for Carousels, Reels, Single_Image (empty) - LinkedIn/Posts/ — Placeholder (empty) - SEO_and_Local_SEO/ — CONTEXT.md (not started)

| ✅ Done - fortunemarq.com is live on Hostinger - Google My Business: created, verified, basic info added - 11 niche HTML landing pages generated (April 2026) — all 11 niches covered - 2 Gemini-generated brand visuals created for niche pages | 🔲 Pending - Deploy 11 niche pages to fortunemarq.com/[niche]-hubli (Hostinger access required) - GMB full optimization: categories, service areas, monthly posts, review strategy - Instagram: bio, first 9 posts, reel strategy - LinkedIn: company page, Jabeer personal page, first 5 posts - SEO keyword targeting for fortunemarq.com - Niche page deployment is a hard dependency for WhatsApp bot replies |
| --- | --- |

| 06 PAID MARKETING | NOT STARTED |
| --- | --- |

PURPOSE: Google Ads and Meta Ads campaigns for FortuneMarq to acquire clients. Strategy is planned. Execution is the last step in the build sequence — campaigns can only start after FMOS is deployed, Afifa is live, and niche landing pages are deployed. Gyms is the planned first campaign niche.

Key Files & Subfolders - Google_Ads/ — CONTEXT.md (strategy documented, no campaigns built) - Meta_Ads/ — CONTEXT.md (strategy documented, no campaigns built) - _project_files/ — Master context and niche data reference

| ✅ Done - Strategy documented: Gyms niche first, then Skin Clinics - Niche data reference sheet available for ad targeting - Campaign sequence planned: landing pages → FMOS live → Afifa live → ads launch | 🔲 Pending - Deploy niche landing pages to fortunemarq.com - Set up Meta Business Manager ad account - Record 1 core video ad per niche (60–90 seconds, Jabeer on camera) - Create ad creatives (thumbnails, copy) in Canva - Launch first campaign — Gyms niche - Week 2: analyze performance, cut underperformers, scale winner - Google Ads campaign setup - ALL campaigns blocked until FMOS deployed + Afifa live + landing pages live |
| --- | --- |

| 07 DATA AND RESEARCH | IN PROGRESS |
| --- | --- |

PURPOSE: The data backbone of FortuneMarq's outreach engine. Contains the full lead database (8,000+ leads across 9 Karnataka cities), keyword research (9 cities × 14 niches), competitor SERP data, and the PDF generator that creates English and Kannada market reports for prospects. Hubli pipeline is complete — other cities are in progress.

Key Files & Subfolders - Lead_Database/ — 858 upload-ready Hubli leads (11 CSVs) + 8 other city folders - Hubli_All_Leads_Clean.csv — Combined 858-row Hubli master CSV - Keyword_Data/ — Master Excel + city-niche keyword folders (9 cities) - Competitor_Data/ — SERP analysis for 6 niches across 6 cities - PDF_Generator/ — Full Python pipeline (English + Kannada PDF generation) - Niche_Data_Reference_Sheet.md — L0 master niche data - DATA_RESEARCH_STATUS_REPORT.md — Current pipeline status - cleanup.py, analyze_leads.py, process_hubli_leads_v2.py — Data processing scripts

| ✅ Done - 858 Hubli leads cleaned, structured into 11 niche CSVs, and imported into FMOS - Hubli_All_Leads_Clean.csv — combined master (858 rows) - PDF Generator pipeline complete and reusable (EN + KN) - 37 English Hubli PDFs generated and approved - Master keyword Excel complete — all 9 cities × 14 niches - Competitor SERP data complete for Hubli across 6 priority niches - Cleaned lead data exists for all 9 cities (Hubli, Dharwad, Belgaum, Davangere, Mysuru, Mangalore, Kalburgi, Vijayapura, Ballari) - Bulk-import tool built in FMOS for one-click CSV upload | 🔲 Pending - Regenerate 38 Kannada Hubli PDFs after fixing misspellings in pdf_generator_kn.py - Upload Hubli_Final/ CSVs to FMOS via /admin/bulk-import (blocked on deployment) - Run Dharwad pipeline — SERP assets ready, just needs processing - Belgaum, Mangalore, Davangere, Ballari — SERP assets partially ready - Mysuru, Kalaburgi, Vijayapura — need SERP HTML collection first - Other city pipelines are low priority until Hubli outreach is fully underway |
| --- | --- |

| 08 FINANCE | IN PROGRESS |
| --- | --- |

PURPOSE: Financial management for the agency — pricing, invoicing, revenue tracking, and GST compliance. Pricing is locked. The FMOS finance module (/admin/finance) is built. No invoices have been raised yet — first invoice will go to first signed client. Current MRR is ₹0.

Key Files & Subfolders - Invoicing/ — CONTEXT.md (first invoice pending first client) - Pricing_Decisions/ — CONTEXT.md (all pricing locked) - Revenue_Tracking/ — CONTEXT.md (₹0 MRR currently) - _project_files/ — Master context

| ✅ Done - All pricing locked and documented in ServiceOfferings wiki - Payment policy locked (50% advance + 50% on delivery) - Revenue model defined: MRR vs one-time split tracked separately - GST details documented (GSTIN: 29ICWPS9816Q1ZS) - Monthly burn calculated: ₹15,600–₹16,600/month - Finance module built in FMOS at /admin/finance | 🔲 Pending - FMOS Phase E: MRR vs one-time revenue split in Finance dashboard - FMOS Phase E: Revenue Forecast Widget (pipeline × close rate vs ₹50K target) - Activate GST invoice settings in FMOS once deployed - Raise first invoice on first signed client - Current MRR: ₹0 (Jabeer's freelance income of ₹15K–₹20K/month is separate) |
| --- | --- |

| 09 LEGAL AND OPERATIONS | COMPLETE |
| --- | --- |

PURPOSE: All legal registrations, agreement templates, service terms, and payment policies. GST and Udyam registration both complete (November 2025). Agreement template, service terms, and payment/cancellation policy are all written. Minor items remain: privacy policy and FMOS GST activation.

Key Files & Subfolders - BUSINESS_MASTER_INFO.md — Complete business identity document - Agreement_Templates/agreement_template.md — 1-page client agreement - Agreement_Templates/service_terms.json — Terms for all 7 services - Business_Policies/payment_and_cancellation_policy.md — Full payment SOP - GST_and_Compliance/GST Certificate.pdf — Official certificate (valid from 05/11/2025) - fortunemarq udyam.pdf — UDYAM-KR-13-0088191 micro enterprise certificate

| ✅ Done - GST registered — GSTIN: 29ICWPS9816Q1ZS (valid from 05/11/2025) - MSME/Udyam registered — UDYAM-KR-13-0088191 - 1-page client agreement template complete (agreement_template.md) - Service-specific terms for all 7 services (service_terms.json) - Full payment and cancellation policy written - Complete business identity documented (BUSINESS_MASTER_INFO.md) | 🔲 Pending - Privacy Policy for fortunemarq.com (not urgent until significant traffic) - Website Ownership Transfer document (for clients exiting website service) - GST invoice compliance checklist for FMOS activation - Enter GSTIN and bank details in FMOS /admin/finance settings (blocked on deployment) |
| --- | --- |

| 10 PERSONAL GROWTH | NOT STARTED |
| --- | --- |

PURPOSE: Jabeer's personal development folder — tracks learning across AI, communication skills, and digital marketing. Three learning tracks are defined. No actual learning logs, resources, or notes exist yet in any subfolder. Runs in parallel with the agency build.

Key Files & Subfolders - AI_Learning/ — CONTEXT.md only (no logs yet) - Communication_Skills/ — CONTEXT.md only (no logs yet) - Digital_Marketing_Learning/ — CONTEXT.md only (no logs yet) - _project_files/ — Master context

| ✅ Done - Three growth tracks defined: AI Learning, Communication Skills, Digital Marketing - CONTEXT.md created for each track with goals and scope | 🔲 Pending - Start logging real meeting insights in Communication_Skills/ - Document AI workflows that work well in AI_Learning/ - Note Meta Ads learnings in Digital_Marketing_Learning/ - This is ongoing — no hard deadline. Build as you go. |
| --- | --- |

| BA BRAND ASSETS | COMPLETE |
| --- | --- |

PURPOSE: The master brand asset library. Contains all 3 logo variants (white, black, and green backgrounds) plus all brand fonts in multiple formats. Used across all documents, landing pages, PDFs, and the website. Fonts: Alliance No.1 and No.2 (primary display), JetBrains Mono (technical), Noto Sans Kannada (Kannada language output).

Key Files & Subfolders - Logo1_whitebackground.jpg — Primary logo on white - Logo2_blackbackground.jpg — Logo on dark/black - Logo3_greenbackground.jpg — Logo on brand green (#42CA80) - FortuneMarq_Brand_Guidelines.png — Brand guidelines reference - degarism-alliance-no1-light.otf/.ttf — Alliance No.1 (primary display font) - degarism-alliance-no2-light.otf/.ttf — Alliance No.2 (secondary display font) - JetBrainsMono-Regular.ttf/.woff2 — Technical/code font - NotoSansKannada-Regular.ttf — Kannada language font (for KN PDFs) - alliance1_fixed.ttf, alliance2_fixed.ttf — Fixed/converted font variants

| ✅ Done - All 3 logo variants exported and available - All 4 brand fonts available in multiple formats (OTF, TTF, WOFF2) - Brand guidelines reference image created - Fonts used across: PDFs, landing pages, FMOS, website - Fixed font variants generated for compatibility with PDF generator | 🔲 Pending - No outstanding items — asset library is complete - Add new assets here if brand evolves |
| --- | --- |

| OR OBSIDIAN RAG (Knowledge Base) | COMPLETE |
| --- | --- |

PURPOSE: The Claude-powered institutional memory system built in Obsidian. Contains 17 wiki pages covering every aspect of the business — strategy, tech, team, decisions, services, data, and roadmap. Feeds context to Claude at the start of every session. Raw input files are stored in raw/ before being processed into wiki pages.

Key Files & Subfolders - cla.md — Claude identity and instruction file (session rules, Jabeer's context) - wiki/index.md — Master index of all 17 wiki pages - wiki/ — 17 pages: FMOS, FortuneMarq, SalesSystem, TechStack, LockedDecisions, etc. - raw/ — 10 raw input files ingested April 28, 2026 - schema/SCHEMA.md — Wiki conventions and workflow governance - scripts/lint.py — Wiki linting script - README.md — System overview

| ✅ Done - 17 wiki pages created and cross-referenced - cla.md finalized with Jabeer's context, working rules, and session checklist - SCHEMA.md governing conventions in place - 10 raw input files ingested on April 28, 2026 - lint.py script available for wiki consistency checking - All locked decisions, open decisions, and blockers documented - Full team structure, tech stack, and growth roadmap in wiki | 🔲 Pending - Keep wiki pages updated as decisions are made and blockers resolve - Ingest session outputs into raw/ then promote to wiki pages - Update FMOS.md once deployment is complete - Update CurrentBlockers.md once FMOS is deployed - Update GrowthRoadmap.md when first revenue is recorded |
| --- | --- |

# Critical Path to Revenue

Everything is built. The following 5 steps, in order, unlock the entire system:

| # | Action | What It Unlocks |
| --- | --- | --- |
| 1 | Deploy FMOS to fmos.fortunemarq.com on Hostinger | EVERYTHING. This is the master blocker. |
| 2 | Create Afifa's account, load ~6,300 leads via /admin/bulk-import | Telecaller can start outreach immediately |
| 3 | Deploy 11 niche landing pages to fortunemarq.com/[niche]-hubli | WhatsApp bot replies can go live |
| 4 | Activate Meta WhatsApp Business API | Automated follow-up messages enabled |
| 5 | Launch Gyms niche paid campaign (Meta Ads) | Inbound lead generation begins |

The machine is built. Deploy and turn it on. FortuneMarq Media & Marketing · Hubli, Karnataka · GSTIN: 29ICWPS9816Q1ZS