## Pending Tasks
FortuneMarq — Pending Tasks Tracker
Generated from project files · May 2026 · 23 tasks
# | Area | Folder | Task Description | Status | Priority | Blocked By | Effort | Owner
1 | CRM & Tool | 01_CRM_AND_TOOL | Deploy FMOS to fmos.fortunemarq.com (Hostinger hosting + subdomain) | BLOCKED | P1 - Critical | Hosting setup | Medium (2–4 hrs) | Jabeer
2 | CRM & Tool | 01_CRM_AND_TOOL | Upload Phase 1 Hubli leads to FMOS (11 CSVs ready, 626 callable leads) | BLOCKED | P1 - Critical | Task #1 — FMOS deployment | Small (30 min) | Jabeer
3 | CRM & Tool | 01_CRM_AND_TOOL | Implement CRM blueprint changes — Outreach Board, Lead Profile, role views, Revenue Forecast | PENDING | P2 - High | — | Large (1–2 days) | Jabeer
4 | Sales System | 03_SALES_SYSTEM | Set Afifa's start date and brief her on calling workflow | BLOCKED | P1 - Critical | Tasks #1 & #2 — FMOS live + scripts ready | Small (1 hr) | Jabeer
5 | Sales System | 03_SALES_SYSTEM | Finalise telecaller scripts for all 14 niches | IN PROGRESS | P2 - High | — | Medium (3–5 hrs) | Jabeer
6 | Data & Research | 07_DATA_AND_RESEARCH | Locate generate_sample_pdf_v3.py on Mac and move into 07_DATA_AND_RESEARCH/ folder | PENDING | P1 - Critical | — | Small (30 min) | Jabeer
7 | Data & Research | 07_DATA_AND_RESEARCH | Update PDF generator to read from _ALL_RESULTS.json (remove hardcoded data) | PENDING | P1 - Critical | Task #6 | Medium (2–4 hrs) | Jabeer
8 | Data & Research | 07_DATA_AND_RESEARCH | Generate all Hubli PDFs (10 niches in _ALL_RESULTS.json — EN + KN) | PENDING | P2 - High | Task #7 | Small (1 hr once script fixed) | Jabeer
9 | Data & Research | 07_DATA_AND_RESEARCH | Create PDF_Index.md — map all 252 PDFs to city, niche, language, filename | PENDING | P2 - High | — | Small (1 hr) | Jabeer
10 | Data & Research | 07_DATA_AND_RESEARCH | Scrape Dharwad Phase 1 SERP data via SearchAPI.io (6 niches) | PENDING | P2 - High | SearchAPI.io budget approval | Medium (3–5 hrs) | Jabeer
11 | Data & Research | 07_DATA_AND_RESEARCH | Fix _ALL_RESULTS.json — add 4 missing niches: IELTS, Modular Kitchens, Tuition, Hotels | PENDING | P3 - Medium | — | Medium (2–3 hrs) | Jabeer
12 | Data & Research | 07_DATA_AND_RESEARCH | Merge keyword volumes from Keyword_Data/ into Hubli Master SERP Report (13 niches show TBD) | PENDING | P3 - Medium | — | Small (1–2 hrs) | Jabeer
13 | Data & Research | 07_DATA_AND_RESEARCH | Investigate and fix 'Has Website' column — all Phase 1 leads show Y, may be data error | PENDING | P3 - Medium | — | Small (1–2 hrs) | Jabeer
14 | Data & Research | 07_DATA_AND_RESEARCH | Delete corrupt Hubli IELTS CSV and re-scrape IELTS Coaching leads from Google Maps | PENDING | P4 - Low | — | Small (1 hr) | Jabeer
15 | Data & Research | 07_DATA_AND_RESEARCH | Finalise leads for remaining 8 cities — start with Dharwad (891 leads, 93% phone) | PENDING | P3 - Medium | Task #10 — Dharwad SERP done | Medium (2–4 hrs) | Jabeer
16 | Data & Research | 07_DATA_AND_RESEARCH | Generate PDFs for all 8 remaining cities once SERP data scraped | PENDING | P3 - Medium | Tasks #10 & #15 | Large (full day) | Jabeer / Zaid / Sufiyan
17 | Data & Research | 07_DATA_AND_RESEARCH | Verify phone recovery count from website_scraper.log and merge recovered numbers into CSVs | PENDING | P3 - Medium | — | Small (1 hr) | Jabeer
18 | Data & Research | 07_DATA_AND_RESEARCH | Fix folder naming inconsistencies: Davangeri→Davangere, Manglore→Mangalore, Kalburgi→Kalaburagi | PENDING | P4 - Low | — | Small (30 min) | Jabeer
19 | Data & Research | 07_DATA_AND_RESEARCH | Remove duplicate files: serpdata/ folder (same as SERP_HTML/), duplicate keyword XLSX in Competitor_Data/ | PENDING | P4 - Low | — | Small (30 min) | Jabeer
20 | Online Presence | 05_FORTUNEMARQ_ONLINE_PRESENCE | Build landing pages for Phase 1 Hubli niches (Zaid & Sufiyan — Antigravity) | PENDING | P2 - High | Zaid/Sufiyan tutorials complete | Large (ongoing) | Zaid / Sufiyan
21 | Paid Marketing | 06_PAID_MARKETING | Set up Google Ads campaigns for Phase 1 Hubli niches once landing pages live | PENDING | P3 - Medium | Task #20 | Medium (1 day) | Jabeer
22 | Team | HR / Ops | Start Afifa — brief on FMOS, calling scripts, outcome logging process | BLOCKED | P1 - Critical | Tasks #1, #2, #5 | Small (2 hrs) | Jabeer
23 | Team | HR / Ops | Complete Zaid & Sufiyan Antigravity training — move to first live build | IN PROGRESS | P2 - High | — | Medium (ongoing) | Zaid / Sufiyan

## Legend
STATUS
BLOCKED | Cannot start — depends on another task/person
PENDING | Ready to start, no external blocker
IN PROGRESS | Currently being worked on
DONE | Completed
PRIORITY
P1 - Critical | Blocks revenue / entire operation
P2 - High | Important, do this week
P3 - Medium | Do this month
P4 - Low | Nice to have / housekeeping